## Employee Award Program Schedule
|  | Enter Start Date: | 2013-05-16
# | Task | Prerequisites | Due Date | Resources | Notes
0 | Be awesome | N/A | Always | You
1 | Decide to launch awesome Employee Award Program | 0 | 2013-05-16 | Employee Awards Program Kit
2 | Create committee for awards | 1 | 2013-05-16 |  | A committee is optional, you could do this all on yourself.
3 | Create awards schedule | 2 | 2013-05-16 | 03 - Example Project Schedule | You may choose to add the award program to a pre-existing meeting, such as a quarterly offsite or yearly meeting.
4 | Decide on award categories | 2 | 2013-05-23 | 04 - Example Award Categories
5 | Decide on winner criteria | 4 | 2013-05-23 | 02 - Employee Awards Guidebook | Decide how you will select finalists and winners.
6 | Create nomination form | 4,5 | 2013-05-30 | 05 - Example Nomination Form | Make sure your nomination form matches how you will decide the winner.
7 | Announce Employee Award Program | 3-7 | 2013-05-30 | 06 - Example Awards Program Emails | Be sure to share the award categories, nomination date, and link to a nomination form.
8 | Open nominations | 6,7 | 2013-05-30 |  | You may decide to send a few teasers about the awards before actually opening up nominations.
9 | Promote nominations | 7,8 | 2013-06-13 | 06 - Example Awards Program Emails | People are forgetful so you'll want to send multiple reminders to nominate coworkers.
10 | Close nominations | 8 | 2013-06-27
11 | Select Finalists | 10 | 2013-07-04 | 02 - Employee Awards Guidebook | Determine how many finalists you will have for each award.
12 | Notify Finalists | 11 | 2013-07-04 | 06 - Example Awards Program Emails | This step is optional but can be a great way to create buzz about your event.
13 | Select Winners | 11 | 2013-07-11 | 02 - Employee Awards Guidebook
14 | Announce Winners | 13 | 2013-07-14 |  | Ideally this is done as a live event, if not, the more personalized the announcement the better.
15 | Award the Winners | 13 | 2013-07-14 | 07 - Digital Certificate | To keep excitement, this can be done at the same time the winners are announced.
16 | Spread the Word | 15 | 2013-07-15 | 06 - Example Awards Program Emails
17 | Congratulate yourself on a job well done | 16 | 2013-07-15
18 | Do it again next year | 0-17 | 2014-05-16
Formulas:
Due Date = [Due Date, row above]
Due Date = [Due Date, row above]+14